## Sheet1
NESSF Project Timeline

#	Task			2018					2019					2020
		Start	Finish	J	F	M	A	M	J	J	A	S	O	N	D	J	F	M	A	M	J	J	A	S	O	N	D	J	F	M	A	M	J	J	A	S	O	N	D
	IRIS EE Study
1	Update EE Dataset	01/18/18	03/18/18
2	Si IV Optical Depth Analysis	03/01/18	09/18/18
3	EE Doppler Velocity Analysis	10/01/18	01/30/19
4	Submit IRIS EE Paper (ApJ)	02/01/18	02/01/18

	ESIS/MOSES-III
5	Optical Alignment and Focus	01/31/18	04/30/18
6	Integration and Testing (MSU)	06/01/17	06/30/18
7	Delivery and Testing (WSMR)	10/01/18	11/2018
8	Launch	11/2018	11/2018
9	Data Analysis/Paper writing	11/2018	08/05/19
10	Submit ESIS/MOSES-III EE Paper	08/06/19	08/31/19
11	Prepare for future launch with two
	additional cameras (to be proposed)	12/01/18	TBD

	MSU PhD Program
12	Prepare Thesis	01/15/17	05/31/20
13	Dissertation Defense	Summer 2020
14	Graduation	Summer 2020